## With Goss
Day No. | Task | Building | Duration (days)
0 | Seek Planning Permision | Factory | 35
0 | Re-arrange Printing of Bugle | Factory | 15
0 | Engage Architect | Warehouse | 7
7 | Draw Up Plans | Warehouse | 10
17 | Plans Approved by Board | Warehouse | 2
19 | Site Clearance | Warehouse | 15
19 | Obtain Full Planning Permission | Warehouse | 20
35 | Alter Roof | Factory | 30